# NeoAgent V2 Campaign Plan

Decision-ready working plan

# Purpose

Make the NeoAgent V2 agent harness useful and understandable. Connect the proposed keynote story, demo slate, performance evidence, and launch materials.

# Campaign outcome

- Lead with work the agent can finish. NeoAgent coordinates an existing model and tools to gather context, carry out bounded tasks, and verify the result.

- Leave the Exec Review with approval on the keynote storyline and alignment on the GTC demo slate.

- Compare every performance result with NeoAgent V1 using the same model, internal workflows, and execution environment.

# Current operating picture

- The agent-first keynote storyline is proposed. Leadership still needs to approve its content and emphasis.

- Mike’s approved V2-versus-V1 results have arrived, but the deck and campaign copy still need updating.

- The marketing shoot is blocked because the planned venue is unavailable. Priya holds Studio B Friday or Studio C Tuesday until 4:30 PM today.

- Social rollout needs a current owner update. Retail demo readiness still needs a final owner.

# Decisions required

## 1. Keynote storyline

Approve the proposed agenda and talking points. Use a recognizable agent workflow to explain why the harness matters, then support it with the scoped comparison.

## 2. GTC demo slate

Choose distinct examples that demonstrate useful assistance and user control. Confirm inclusion and owners for the workplace, partner, and retail candidates. No final slate is approved yet.

## 3. Performance evidence and review scope

NeoAgent V2 achieved 92% task success versus NeoAgent V1’s 80% (+12 percentage points). Median completion time was 30% lower and model tokens per completed task were 25% fewer than V1. Both used the same 200 internal workflows, model, and environment. These fictional demo figures are cleared for leadership review only. Final external copy needs Legal review.

## 4. Marketing shoot date

Choose a replacement date so Priya can rebook the venue and preserve downstream crew holds.

# Workstreams

## Exec Review deck

- Update slide 4 with Mike’s approved V2-versus-V1 comparison. Retain the V1 baseline, “median,” “per completed task,” and internal evaluation scope.

- Summarize the local laptop comparison and associate-reviewed follow-up from slide 6 in slide 7’s Customer Example section, then remove slide 6 from the live flow.

- Protect slide 10 for the two decisions: keynote storyline and GTC demos.

## Agent Messaging

- Apply the same approved comparison as the deck. Keep the baseline, metric definitions, and review scope intact.

- Explain how the harness plans, selects context, uses tools, and checks results. Local model processing does not make Google Workspace access offline.

## Campaign operations

- Obtain Rafael’s social rollout update and confirm a final retail demo owner.

- Capture the marketing shoot date decision and unblock venue and crew booking.

- Record decisions and durable status changes in the Second Brain.

# Working files

Campaign tracker: SHEET_URL

Exec Review deck: DECK_URL

Benchmark evidence: Mike Chen’s approved comparison and Daniel Cho’s leadership-review clearance.

# Operating rule

Refresh current email, Calendar, and Second Brain evidence before changing status. Record the source and approval scope for changes. Use human titles and verified links in project writing.