## Campaign Lanes
RTX Spark Campaign Tracker
Decision-ready view of campaign execution • Updated
Awaiting updates | 4 |  | Blocked | 2 |  | Active lanes | 8 | Last refreshed | 2026-08-13
Statuses are updated from current owner evidence; use the Artifact column to open the working file or decision source.
Lane | PIC | Status | Latest update | Next action | Due | Dependency / blocker | Evidence | Artifact | Notes
Product specifications | Mike Chen | In progress | Mike supplied approved product specifications: Blackwell RTX GPU: Up to 6,144 cores; Grace CPU: Up to 20 cores; FP4 AI performance: Up to 1 petaflop; Unified memory: Up to 128 GB. | Keep “up to” with every specification and retain FP4; route final external copy through Legal. |  | Campaign-wide Legal approval remains pending. | Mike Chen email — EMAIL_MIKE; Daniel Cho email — EMAIL_DANIEL | DECK_URL
Exec Review deck | Elena Park | In progress | Slides 4, 7, and 9 now contain the approved leadership-review figures, retail-owner dependency, and shoot-slot options. | Remove slide 6 from the live flow manually and confirm the specifications package remains current before presenting. |  | Slide 6 still requires manual removal; retail demo owner remains unassigned. | Updated deck — DECK_URL | DECK_URL
Agent Messaging | Workspace Owner | Awaiting update | Mike supplied the approved product specifications; Agent Messaging has not yet been updated. | Apply the approved specifications, retaining “up to” and FP4, then route external copy through Legal. |  | Campaign-wide Legal approval remains pending. | Mike Chen email — EMAIL_MIKE; Daniel Cho email — EMAIL_DANIEL | DOC_URL
Marketing shoot | Priya Nair | Blocked | The latest available note offers Studio B Friday or Studio C Tuesday, but its hold timing is historical and current availability is unverified. | Reconfirm venue and preferred-crew availability with Priya, then choose the replacement slot. |  | Replacement slot is undecided and current availability is unverified. | Priya Nair email — EMAIL_PRIYA | SHEET_URL | Missing the hold risks a four-business-day campaign slip.
Partner enablement | Aisha Rahman | On track | The VP requested a review of the Hermes partner slides, and the staged OpenShell Windows/WSL pilot passed its smoke check and is ready for an inclusion decision. | Review the Hermes partner section and decide whether OpenShell belongs in the partner demo while aligning commitments to the approved keynote and demo slate. | 2026-08-04T17:00:00-07:00 | Keynote and GTC demo-owner decisions remain open. | Elena Park email — EMAIL_ELENA; OpenShell Program email — EMAIL_OPEN_SHELL | DECK_URL | OpenShell passed smoke testing; production inclusion is not yet approved.
Social rollout | Rafael Costa | Awaiting update | No current status has been received. | Request asset readiness, timing, and blockers from Rafael. | 2026-08-03 | PIC status | Email / Slack |  | Follow-up draft needed.
Retail demo readiness | Grant Walker | Blocked | Aisha still had no final retail demo owner in the latest available update; no reply has arrived to the current follow-up. | Assign the final retail demo owner and confirm owner coverage during the Exec Review. |  | Final retail demo owner is unassigned. | Aisha Rahman thread — EMAIL_AISHA | DECK_URL | No direct current update from Grant was received; status reflects the sourced lane-level owner gap.
Legal intake LGL-2026-0847 | Daniel Cho | In progress | Daniel cleared Mike’s product specification wording for leadership review only. | Keep “up to” and FP4 intact and route final external campaign copy through Legal for campaign-wide clearance. |  | Campaign-wide clearance remains pending. | Daniel Cho email — EMAIL_DANIEL | SHEET_URL